SCHENECTADY LIGHT OPERA COMPANY

2019 - 2020

PRODUCTION HANDBOOK

Board Approved: 5/7/19       Last Updated: 5/5/2019

TABLE OF CONTENTS

INTRODUCTION 2 MISSION STATEMENT 2 KEY ROLES, RESPONSIBILITIES & CONTACTS 3 GENERAL TIMELINE & PROCESS OVERVIEW 4

GETTIN' READY 5 SET DESIGN APPROVAL PROCEDURES 5 AUDITIONS 5 BUDGET & FINANCE PROCEDURES 5-6 HIRING MUSICIANS 6 PREFERRED VENDER LIST 7 EXPENSE/PAYMENT OPTIONS 8

REHEARSALS, FACILITY & BUILD RULES 9-10 READ-THROUGH AND REHEARSAL SCHEDULE 9 FACILITY USE RULES & GUIDELINES 9-10 CONSTRUCTION GUIDELINES 11-12 ACCIDENTS & INCIDENTS 12 WHAT TO DO WHEN THINGS AREN’T GOING WELL 12-13

THOSE OTHER DETAILS  13 MARKETING & PUBLICITY 13 CRITIQUE AND DRESS/TECH 13-14 PLAYBILL PROCESS AND BOX OFFICE & TICKETS 14-15 CURTAIN SPEECH REQUIREMENTS 16 CLEANUP DAY 17

PERFORMANCES 18 WHO’S IN CHARGE AND WHAT DOES THAT MEAN? OPENING NIGHT, VIDEOS AND CABARETS  18

WRAPPING IT UP 19 STRIKE & CAST PARTY, CAST & CREW FEEDBACK SURVEYS, PRODUCTION RECOGNITION AND T-SHIRTS 19

BOARD/LEADERSHIP JOB RESPONSIBILITIES 20-24

CRITIQUE GUIDELINES AND WORKSHEET 25-26

NECESSARY PAPERWORK AND ADDITIONAL INFORMATION 27-49

INTRODUCTION

This handbook is a guide for all individuals responsible for a production or production department at SLOC during the 2019 - 2020 season. This handbook will be updated on an annual basis; any suggestions for changes should be sent to artisticdirector@sloctheater.org to be approved by the Board of Directors.

It is the duty of each production's Producer and Director to thoroughly understand the requirements and expectations laid out by the Board of Directors in this document. These individuals are ultimately responsible for communicating requirements and expectations clearly to all members of their teams and ensuring that the conduct of all team members upholds the highest standards of safety, collaboration, ethical integrity and artistic quality.

SLOC intentionally leaves many process details open for each production team to customize as needed. This handbook specifically outlines those key areas where standard practices are critical to meet broader organizational needs, ensure volunteer safety, protect the facility and to maintain a consistently positive experience for volunteers of all productions.

MISSION STATEMENT

SLOC Musical Theater is a non-profit community-based performing arts center. Our mission is to provide opportunities for adults and youth to experience and participate in the performing arts.

KEY ROLES, RESPONSIBILITIES & CONTACTS

Artistic Director: Serves as general contact and advisor to all productions and oversees production committees as well as critique for each production

2019-2020: Trish Scott-Dembling artisticdirector@sloctheater.org

Audience Services Director: Manages all front-of-house needs, including box office, house managers, ushers and opening night parties

2019-2020: Jeffrey P. Hocking audienceservices@sloctheater.org

Audition Coordinator: Organizes and runs SLOC’s auditions in conjunction with production team

2019-2020: Susan Skinner srskinner@gmail.com

Board Liaison: Acts as the conduit between the Board of Directors and the production staff. Responsible for ensuring that teams are aware of, and in compliance, with SLOC’s policies and procedures. If necessary, also serves as a resource to assist with conflict resolution and to seek additional support for the production

Box Office Manager: Runs daytime (and oversees night-of-show) subscriptions, sales and donations

2019-2020: Jeffrey P. Hocking tickets@sloctheater.org

Director: The final artistic voice for the production. It is the Director’s duty not just to create a successful show, but also to establish a safe, healthy, fun and collaborative working environment

Facility Chair: Oversees the buildings and property where SLOC is located.

2019-2020: Mike Deyo maddeyo23@yahoo.com

Finance Chair: Oversees SLOC’s budget, expenses and legal requirements. All show budget proposals must be approved by the Finance Committee for a production to proceed with major expenses.

2019-2020: Kelly Sanford finance@sloctheater.org

Public Relations and Advertising Director: Organizes season and show-specific promotional placements, social media marketing and all printed marketing materials including the season brochure.

2019-2020: Audrey Carlton pr@sloctheater.org

Playbill Editor: Collects and edits all info for production programs and oversees the design approval process.

2019-2020: Jeffrey P. Hocking playbill@sloctheater.org

Producer: Ensures the production process runs smoothly, complies with SLOC procedures and meets financial goals. Submits the show budget and tracks expenses. Other responsibilities at discretion of production team.

Production Recognition Coordinator: Orders production team thank you memorabilia

2019-2020: Paula Farquharson Ps29mather@icloud.com

Technical Director: Oversees SLOC’s production technical departments (and crews) including costumes, props, hair and makeup, lights, providing long-term theater tech planning, season technical operations and emergency show production support.

2019-2020: Matthew Dembling technicaldirector@sloctheater.org

GENERAL TIMELINE & PROCESS OVERVIEW

• Show Proposal Submission

o Late summer, prior season (see SLOC Facebook & website for details)

• Live Show Proposal w/Show Selection Committee

o Fall, prior season. Potential Directors will be contacted to schedule interviews

• Season Announcement

o Winter, prior season. Directors will be contacted before public notice.

• Design Submission

o Due no later than three months prior to opening. Approval required before construction.

• Auditions & Casting

o Auditions should be scheduled approximately 3 months before opening. Contact Audition

Coordinator to schedule auditions and set processes.

• Budget Proposal Submission

o Due 3 months prior to opening. Approval required before major expenses made.

• First Rehearsal & Read-Through

o About 2 1⁄2 months prior to opening and immediately before regular rehearsals begins.

• Rehearsals in the Education Building

o Roughly covers the first month of rehearsals. Standard rehearsal days are Monday PM,

Wednesday PM, Friday PM and Sunday PM. Exact times to be decided by production staff.

• Rehearsals in the Theater

o Begins the day following strike of the previous show.

• Playbill Submission

o All playbill materials are due to the playbill editor approximately 1 month prior to opening.

See page 20 for details and exact due dates.

• Publicity Photo Shoot

o Scheduled with Producer and Marketing and Communications Chair. SLOC provides

photographer. At least 2-3 weeks prior to opening.

• Critique

o No later than 10 rehearsals before opening

• Clean-Up Day

o Typically the Saturday before opening (day before Double Tech) but this is negotiable

• Tech and Dress Rehearsals

o Double Tech rehearsal on the Sunday prior to opening, followed by a minimum of 2-3 full

dress runs. Mandatory preview with audience on Thursday before opening at 8PM

• Opening Night

o First Friday night followed by an opening night party in the Education Building.

• Performances and Cabarets

o Performance runs for two weekends (Fri, Sat, Sun, Thu, Fri, Sat, Sun) with curtain at 8 pm

Thursdays, Fridays and Saturdays. 2 pm on first Saturday and Sundays. o After-show Cabarets are generally scheduled after each Saturday performance, but are at the

discretion of the production staff

• Closing and Strike o Strike occurs immediately after final curtain of closing performance.  All cast and crew are expected to participate.

GETTIN' READY

SET DESIGN APPROVAL PROCEDURES

Contact: Artistic Director and Technical Director

Sketches and/or a model of the set design must be approved no later than three months prior to opening by SLOC’s Artistic Director and Technical Director.  Audience Services Director must be consulted if changes to house seating may occur. Sets should be confined to the main stage area, unless the SLOC Board approves otherwise. This is partially to meet NYS Building Code rules specific to our fire safety system.

Audience seating is set by the Director of Audience Services and SLOC Board of Directors. Any desired changes must be approved at least three months prior to opening (preferably earlier) so that seating charts can be changed and subscribers can be accommodated.

AUDITIONS

Contact: Audition Coordinator

All arrangements must be discussed with the Audition Coordinator before announcing audition dates. The Audition Coordinator will work with you to select dates as well as the best process for your show. Please understand that there are broader organizational goals and logistical needs to consider and you may be asked to adjust your process requests.

Please provide at least two different audition dates and limit call-backs to a single date, when possible, as this can be very challenging time to schedule for actors with other jobs/commitments.

Once the dates and process have been determined, please send your audition announcement to info@sloctheater.org at least 6 weeks prior to the first audition date. Samples from previous shows can be provided upon request. The Audition Coordinator will work with the Marketing and Communications Chair to create the appropriate social media events and postings, submit to media contacts and forward the announcement the capdist-auditions list serv on your behalf. Please do not announce auditions on your own or publicize your audition dates before SLOC does.

Please contact ALL audition candidates, not just those cast, by phone or email. This helps build a strong community relationship and encourages performers to attend other auditions. Please include future audition dates if possible.

Final cast lists should be submitted to the Marketing and Communications Chair so that a formal public announcement can be made. Do not share your cast list before SLOC does.

BUDGET & FINANCE PROCEDURES

Contact: Finance Director

BUDGET PROCESS OVERVIEW

Your show budget proposal is due roughly around the time of your auditions. The Producer should contact the Finance Chair to determine the exact date relative to the committee’s meeting schedule.

Both a blank and draft budget worksheet are provided in the Appendix for your convenience.

Each show is allotted $7,500 to cover production expenses: musicians, set materials, costumes, wigs, makeup and special lighting, sound or effects needs. The production team may break this total up as they see fit, though the Artistic Director and Finance Chair may make suggestions and retain veto authority. Any production budget in excess of $7,500 must be approved by the entire Board of Directors. SLOC is here to support high quality community theater productions, but please understand that limited funds exist to cover additional requests, so please consider your needs and wants very carefully before submitting a higher budget. Production teams are encouraged to use the tools, equipment, set pieces, props and costumes that SLOC already owns as much as possible.

Expenses for royalties, rentals, scripts, scores, publicity and marketing material, primary head shots and photo shoot photographer, program design and printing are the responsibility of the company and need not be part of your production budget.

The Finance Chair may ask the producer for an update monthly until the production is completed. The updates should be brief and are meant only to capture significant changes to anticipated final costs.

HIRING MUSICIANS

SLOC has a contract for musician rates. Each musician must be paid a fixed fee of $550, which includes eight performances and a limited number of rehearsals as specified by the Music Director. The number of musicians included in the budget is at the discretion of the Producer and Director. The Music Director receives compensation of $500 in addition to the standard musician compensation they earn if also serving as a member of the orchestra.  This $500 is paid by the company and does not come out of the production budget.

A Musician’s Agreement Form and a Music Director’s Agreement Form are included in the Appendix. Every Musician and Music Director must complete and sign their respective form in order to be paid. It is the Music Director’s duty to distribute and collect these forms. Signed copies must be submitted to the Finance Chair or Bookkeeper’s mailbox no later than the Sunday prior to the opening in order guarantee payment at the closing performance.

PREFERRED VENDORS

SLOC has a list of preferred vendors. Whenever possible, please use these companies:

COSTUMES

MARLU COSTUMES www.marlucostumes.com • (845) 355-1414 • Port Jervis

THE COSTUMER www.thecostumer.com • (518) 464-9031 • Schenectady NY • Albany

LIGHTS & SOUND

ALBANY THEATER SUPPLY www.albanytheatersupply.com • (518) 465-8894 • Albany

BMI SUPPLY www.bmisupply.com • (518) 793-6706 • Queensbury

SETS

ADIRONDACK SCENIC, INC. www.adkstudios.com • (518) 638-8000 • Argyle

NES RENTALS / ALBANY LADDER COMPANY • (518) 869-5335 • Colonie

ALBANY theater SUPPLY www.albanytheatersupply.com • (518) 465-8894 • Albany

STOCK BUILDERS SUPPLY www.stockbuildingsupply.com • (518) 355-7190 • Schenectady

BMI SUPPLY www.bmisupply.com • (518) 793-6706 • Queensbury

GOODSPEED OPERA (rentals) www.goodspeed.org • (860) 873-8664 • East Haddam CT

HOME DEPOT www.homedepot.com • (518) 382-8371

LOWE’S www.lowes.com • (518) 382-8371

ROSE BRAND (fabrics - good prices and service) www.rosebrand.com • 1-800-223-1624

SCHENECTADY HARDWARE & ELECTRIC www.sheinc.com • (518) 346-2369

SHERWIN-WILLIAMS (paint) www.sherwin-williams.com • (518) 374-4406

SYRACUSE SCENERY & STAGE www.syracusescenery.com • (315) 453-8096 • Liverpool

TOBINS LAKE STUDIOS (drops) www.tobinslake.com • (888) 719-0300 • Brighton MI

MISCELLANEOUS

U-HAUL (moving) www.uhaul.com • (518) 382-3210

AMAZON PRIME (tax exempt Prime account) https://www.amazon.com • Contact the Finance Chair for login information. TARGET (tax exempt account) https://www.target.com • Contact the Finance Chair for login information.

EXPENSE PAYMENT OPTIONS

There are three ways to pay for your budget production expenses: a dedicated SLOC store account, a pre-paid SLOC PEX debit card or personal funds submitted for reimbursement.

All production expenses should be written on the appropriate Production Expense Tracking Sheet (see Appendix) in order to track each department’s expenses.

• Each Producer will have an overall Production Expense Tracking Sheet in order to track all expenses for a given production.

• Each department will have their own specific Production Expense Tracking Sheet to be used to track their individual expenses.

o All original receipts must then be provided to the Producer for tracking on their overall

Production Expense Tracking sheet.

• At no time should a production expense receipt be provided to the Finance Committee prior to the end of a show, unless the expense is paid out of pocket and the payer requires reimbursement prior to the end of the show.

o If this scenario occurs, the Producer must fill out an Expense/Reimbursement Reconciliation

form (see appendix) and staple the original receipt to the form.

▪ The form must then be placed in the clear bin hanging on the door of the business office for the accountant to process.

All receipts, including internet transactions, must contain the date of purchase, the vendor, the item purchased and the purchase price. If purchasing from an individual, obtain a written statement from the seller that contains the same receipt information and provide the individual’s name, phone and email address for verification.

● Dedicated SLOC Store Account

o SLOC has direct bill accounts with Home Depot, Lowe’s and The Costumer. o For details, talk to the Technical Director or Finance Chair o Tax-exempt form already on file with the store.

● Pre-Paid SLOC PEX Debit Card

o Recommended for most non-set expenses as it minimizes wait for reimbursement. o Each production team gets a set of cards for dedicated purposes: costumes, lights, makeup, props, set,

sound and miscellaneous (for Producer use). o Spending limits per card will be established by the Finance Committee when the budget is approved.

Spending limits are rarely the full budgeted amount. Additional funds can be added to cards if needed. In this case, the Producer should contact the Finance Chair, who will coordinate with the PEX Card Coordinator in the committee. o Cards will be provided, generally within two weeks of budget approval, to the Producer for distribution to

the production team. o The cards can be used online, but please note that the billing address on record is SLOC’s physical mailing address: 427 Franklin Street, Schenectady, NY 12305.

o Some preferred vendors have a SLOC account on file and recognize the debit cards as official funds. o ALWAYS be prepared to provide a Tax Exempt Certificate if needed. Certificate in Appendix.

● Personal Funds

o SLOC will reimburse personal expenses by check (not cash) as approved by Producer with a Payment

Authorization Form. This is DISCOURAGED as reimbursement times vary. o If a personal expense is necessary, then it is the purchaser’s duty to:

▪ Supply a Tax-Exempt Certificate to the vendor prior to sale. SLOC will NOT reimburse any sales tax made by the purchaser due to negligence.

▪ Keep personal expenses separate from SLOC expenses and retain copies of all SLOC receipts. SLOC reserves the right to reject any receipt that also includes personal expenses.

▪ Keep personal copies of reimbursement requests and backup receipts.

REHEARSALS, FACILITY & BUILD RULES

READ-THROUGH

Contact: Artistic Director

First rehearsal and read-through are typically no later than two months prior to opening and immediately before regular rehearsal schedule begins. Advance read-throughs with a delay before rehearsals should be avoided (Generally script rentals arrive approximately 3 months prior to opening)

Artistic Director will attend, introduce themselves and will hand out the Code of Conduct and Media Release Forms to ALL team participants, both cast and crew. (For underage actors, SLOC requires a parental permission form). Signed copies are required prior to rehearsals in the theater or any publicity shots/footage. Ensuring everyone has signed is the responsibility of the Producer. Copies of these blank forms are included in the Appendix and will be kept in a binder in the board room managed by the Artistic Director.

It is highly recommended that a full rehearsal schedule is provided to cast at this time. Only necessary changes should be made throughout the process to maintain a cross-show standard of dependability and good planning.

Please allow a few minutes for a Board member to welcome the team prior to the start of the read-through as well as the Artistic Director.

REHEARSAL SCHEDULE

Contact: Artistic Director

Roughly speaking, for the first month, rehearsals are in the Education Building. Upon strike of the current show, your production will move into the theater for the remaining rehearsals. Members of your team are expected to coordinate your move-in needs with the previous show’s strike needs.

SLOC’s standard rehearsal days are Monday PM, Wednesday PM, Friday PM and Sunday PM. Exact times can be determined by the production staff, but we ask that you keep the days of rehearsal consistent to our standard schedule as much as possible. This allows standard set and crew work nights on Tuesdays, Thursdays and Saturdays. Using the standard days also minimizes space conflicts with other productions, rentals and facility use.

Please avoid three or more consecutive days of rehearsal.

Your Board Liaison or Producer should coordinate any possible schedule conflicts/rentals in the rehearsal space with the Business Manager (who maintains the calendar).

FACILITY USE RULES & GUIDELINES

Contact: Artistic Director and Technical Director

GETTING IN & OUT OF THE BUILDINGS

There are separate key codes for the lock boxes outside the back entrance of the Education Building, the backstage entrance of the theater and the set facility on Taurus Road. These codes (with the exception of Taurus Road) will be changed after every show. If no one on your team knows these codes, please contact the Artistic Director. PLEASE LIMIT HOW MANY TEAM MEMBERS HAVE THESE CODES. Typically, the Director, Producer, Stage Manager, Music Director and Choreographer are given the codes. Under no circumstance should the codes be given to your entire cast.

All doors should be locked 15 minutes following a rehearsal’s start time. Cast and crew who arrive after this time should knock, call, or text to gain access to the theater or education building.

WHO’S IN CHARGE AND WHAT DOES THAT MEAN?

During Rehearsals (in order of authority):

1. Director 2. Music Director 3. Choreographer 4. Producer 5. Stage Manager 6. Any person designated by the Director or Producer

The Production Team must identify a team member to be responsible for the following items at each rehearsal:

● Opening a building

o Turn on lights in areas of the building/s which will be used

● Using a building

o Making sure all work follows safety protocols o Making sure the facility is not damaged, including but not limited to structural integrity, plumbing,

electrical systems and finish work (paint, carpets, polished wood, etc.) This point is mainly intended for set building days o Making sure, with the help of the rest of the team, that no unauthorized persons enter o Filing any incident or accident reports o Ensuring the team provides all minor housekeeping tasks necessary to keep the space in safe and neat

order and that public spaces are always appropriate for public view. This includes emptying all garbage cans on a regular basis. Garbage should be brought to the dumpster in the theater parking lot.

● Closing a building

o Make sure no one is left in the building o Turn off all but the necessary ghost/running lights (get training from Artistic Director) o Confirm that all entrances are closed and locked

GENERAL SAFETY

● All production staff must become familiar with the location of the fire extinguishers throughout the facility, and with emergency procedures for medical emergencies and alarm activations. The Producer is responsible for the training of the production staff on these safety procedures. Refer to the map in the Appendix for the complete diagram of fire extinguisher locations.

● All doors shall be locked 15 minutes after a rehearsal’s start time. Cast and crew who arrive after this time should knock, call, or text to gain access to the theater or education building.

● During all rehearsals and performances, emergency exit signs must be lit.

● Nothing may obstruct any aisles in the theater during any performance.

● Smoking is not permitted at any time in any of the SLOC buildings. Discarding of cigarette butts on SLOC grounds is not permitted. People who wish to smoke must use the ash cans provided and must smoke outside of the buildings.

● Alcohol consumption during any performance, rehearsal or work call by any member of the cast or crew of the current production is prohibited.

● The cast and crew are responsible for cleaning up any spills that occur. Cleaning supplies are located backstage in the bathroom. Everyone should do their part to pick up after themselves whenever they are on the SLOC property, indoors or outdoors. Nothing should be left out of place. All tools and cleaning equipment should always be stored in their appropriate place. All garbage cans must be emptied on a regular basis. Garbage should be taken to the dumpster in the theater parking lot. A clean and organized facility is a MUST, not least because theater donors, potential rental clients and news people may request a tour of the buildings at any time.

● Specialty rooms and storage areas, such as the box office, lighting balcony, costume area, prop area, and make- up cabinet, should be considered off limits to all parties, except those who have a need to be there, or have been granted consent from the Chair of that department.

● Theft concerns are taken very seriously at SLOC. For safety reasons, the exterior doors must be locked during all rehearsals and work days. Cast and crew members should be informed of all the entrances for each of our three buildings. Cast and crew should be advised to lock their vehicles and not to leave any valuables inside, to cover items in their vehicles with blankets or towels, and to walk in pairs when leaving the building after rehearsals or performances.

CLEANUP

Trash removal is the responsibility of each show’s cast and production team. Team members should be instructed and enforced to remove any personal trash they bring in. Ideally, this should become part of the end of every rehearsal process or work day cleanup. When the inside garbage cans are full, please make sure that trash gets moved to the dumpster behind the theater. We expect all team members to replace emptied trash cans with new trash bags, which can be found backstage in the bathroom and in the kitchen of the Education Building. All garbage in the dumpster must be bagged and tied or SLOC may incur additional fees.

SLOC RECYCLES. DO NOT THROW AWAY RECYCLABLES. All recyclable cans must be rinsed and placed in one of the recycling bins backstage or in the kitchen/hall of the Education Building.

HEATING/COOLING

If you want to adjust the heat, go to the thermostat (audience right of theater on the support post and in the back room, adjacent to the stage). The recommended setting is 68 degrees. Please note that the theater is large and takes time to heat up. The furnace will reset, automatically, to the programmed level after 2 hours. If you want to request an increase in the temperature, beyond what is provided by the 2 hours override, you should contact the Facilities Chair for assistance.

Air conditioners are controlled from the light booth and should be used very sparingly. Since they are quite loud, we recommend that they are turned off during the run of performances.

SNOW REMOVAL

SLOC has limited help in shoveling snow around the facility. If there is snow upon arriving at the facility, it is expected that someone from the cast or crew will clear paths. Salt can be found in the Education Building.

PARKING

Refer to the parking map in the Appendix for nearby parking places during rehearsals and work days. The lot behind the theater, adjacent to the Education Building, is available for cast and crew use but is not large enough to accommodate everyone.

Cast and crew should be informed NOT to park in either of the small SLOC parking lots (the Annex parking lot or behind the theater) during performances as these lots are reserved for our elderly and handicapped audience members. There is public parking available on Liberty Street, Franklin Street and in the lot between Liberty and Franklin Street. The Producer should monitor and reinforce parking policies and procedures.

CONSTRUCTION GUIDELINES

Contact: Technical Director

GENIE & LADDER RULES

When using the Genie or ladders, at least two trained, qualified people (including operator) must be present in the theater. UNDER NO CIRCUMSTANCES is anyone allowed to use the Genie or ladders while alone.

STAGE MEASUREMENTS

Please see the attached diagram in the Appendix.

SET RULES

● As much as possible, set construction is to take place at SLOC’s set facility on Taurus Rd.

● CONSTRUCTION AND/OR PAINTING in the carpeted area of the theater is STRICTLY PROHIBITED.

● Minimal set construction can take place on the stage. Please do any cutting work outside, or if absolutely

necessary inside, on sawhorses in a designated area. This is to protect the stage floor.

● Prior to the production’s first dress rehearsal, the set MUST be inspected by the Technical Director for safety

considerations.

● All stairs and risers must be firmly and securely constructed. Whenever possible and practical, all stairs must have

at least one weight-bearing railing. All stairs and risers must be edged in glow tape.

● Prior to set construction, all of audience chairs must be covered with plastic sheeting. These chairs must remain

covered with plastic sheeting to minimize the dust accumulation on them.

● The piano must be covered with plastic sheeting before and during any set construction.

● Theater speakers may not be moved or adjusted without approval from Technical Director.

● No drilling or painting the theater walls or ceilings, front or backstage, unless approved by Board.

● Prior to painting, the carpeted area in front of the stage must be covered with plastic sheeting.

● Use of any oil-based paints or semi-gloss paints on the set, house walls, or floor is prohibited. Only flat latex paint

is allowed at SLOC.

● All tools, paint brushes and trays, ladders and SLOC equipment shall be appropriately cleaned and put away in

their proper storage areas following use.

● Construction debris must be removed from the building during cleanup. Any approved significant holes created in

the stage floor, walls or ceiling must be carefully patched, painted and restored to their former state following completion of the production.

ACCIDENTS AND INCIDENTS

Contact: Board Liaison

If a serious accident occurs to any person in any SLOC building, CALL 911 IMMEDIATELY. Provide the following addresses to emergency services:

Theater – 425 Franklin Street, Schenectady NY 12305

Annex – 427 Franklin Street, Schenectady NY 12305

Education Building – 418 Liberty Street, Schenectady 12305

Set Facility – 261 Taurus Rd, Schenectady NY 12304

Have someone wait outside of the building to provide directions to emergency personnel. If injury is minor, you may use the first aid supplies in the backstage entry room, kitchen of Education Building, or Box Office.

For all accidents and injuries, the Producer, Director, Stage Manager or other person left in charge must complete and file a SLOC Incident Report on the day of the incident. Copies can be found in the SLOC administration office on the second floor or in the Box Office. A sample form is attached in the Appendix. Report any injuries to the President as soon as possible, but no later than 24 hours after the incident.

WHAT TO DO WHEN THINGS AREN’T GOING WELL

Contact: Board Liaison

Please make sure all cast and crew are aware of their right to address issues quickly and directly and with appropriate discretion to a third-party team member higher up the chain of command. If you are brought a problem, please weigh the potential scope of the issue and all possible consequences of a direct intervention. Do not hesitate to ask your Board Liaison for guidance as it is their responsibility to provide troubleshooting support for intra or inter-production problems.

General chain of command is:

1. Cast & Crew 2. Stage Manager 3. Assistant Director 4. Director 5. Assistant Producer 6. Producer 7. Board Liaison 8. Artistic Director 9. President of the Board

The SLOC Board of Directors reserves the right to remove any production team member or cast member from any show if necessary.

THOSE OTHER DETAILS

MARKETING & PUBLICITY

Contact: Public Relations and Advertising Director

SLOC will provide the printed marketing materials for your production. The show billboard will be hung at the close of the show prior (for the September slot, the billboard is typically hung in mid-August). Business cards and posters will be available within the first few weeks of rehearsal. The PR Director will reach out to the production team prior to printing the billboard/posters to ensure spelling, etc. is correct before those materials are printed. All digital marketing will be done through the SLOC Facebook (facebook.com/SLOCTheater), Instagram @SLOCTheater), and Twitter (@SLOCTheater) accounts. Cast members and production team should share SLOC-approved posts only. If a cast or crew member wants to develop their own marketing materials, it must be cleared by the PR Director before posting and sharing. All media contact should be arranged in conjunction with the PR Director.

PUBLICITY PHOTOS

Contact: Public Relations and Advertising Director

To be scheduled with Producer and PR Director so that SLOC’s photographer can be on-site. Typically, this day includes head shots for new SLOC volunteers, promotional shots in costume, and a photo of the cast and crew to be used in the playbill. Updated head shots for returning volunteers are subject to the show's budget and photographer's availability. Existing headshots are stored in the Board Room and should be used whenever possible. Contact boardsecretary@sloctheater.org if you need help locating these. For efficiency, please prepare short lists of promotional shots and an ordered list of cast/crew for head shots. This responsibility typically falls to the Producer.

CRITIQUE

Contact: Artistic Director

Critique is mandatory and is an opportunity for the production staff to receive feedback about the progress of their show from the SLOC Board of Directors and production staff from the season. It is meant to ensure the show is on track for opening and that every artistic opportunity is being exercised. It is understood that the show may not be in final show condition. It is not expected that all technical elements such as costumes, lights, sound or the full set will be complete at this point, but key design elements should be in place. The date for critique should be chosen as soon as possible after the show is cast and the rehearsal schedule set (choose a date where you have the fewest cast member conflicts). It should be late enough to include key design elements but no later than ten rehearsals before opening so changes can be successfully implemented. Please coordinate date and invitation list with the Artistic Director. The cast should perform a full run of the show and then will be dismissed. The critique discussion will begin immediately following the run. The Artistic Director or their designee will run critique and it’s recommended that it is kept under an hour. All Directors and Producers for the season are expected to attend each of the season’s critiques (as schedules allow). Music Directors and Choreographers are highly encouraged to attend as well. Additional attendees may be invited at the request of the director only.

DRESS & TECH

Contact: Artistic Director

Standard SLOC schedules call for a double tech (two full runs and a meal break) the Sunday prior to opening. We highly recommended that you hold at least three full dress runs. Preview audiences are scheduled on the Thursday before opening, at 8PM. The production team may invite other preview guests in addition to SLOC’s preview groups but please use discretion.

PLAYBILL PROCESS

Contact: Playbill Editor

The following items should be provided to the Playbill Editor by the due dates on the next page. Information can be emailed directly to playbill@sloctheater.org (bios should be submitted using the website noted below). Please keep in mind that these due dates are set so that there is time to edit the information and forward it on to the Playbill designer. The designer then creates the Playbill and sends a proof back to the Producer for approval. The dates listed in this section are hard deadlines and cannot be extended. There is an editing process in which minor changes can be made, but all the below items please be submitted by the deadline.

• Cast List: The entire cast of actors in order of appearance including actor and character names.

• Production Staff: This should list EVERYONE involved in creating the show. Producer, Director, Music Director, Stage Manager, Designers, Set Construction, Set Painting, Stage Crew, Light/Sound Board operators. Everyone that you would like to receive credit for their participation on this project.

• Bios are required from all actors and major production staff (ie, Director, Producer, Music Director, Stage Manager, Light/Set/Sound/Costume/Hair/Make-up Designers, etc). Generally, SLOC does not include bios for assistant designers, stage crew, set construction/painting, light/sound board ops, musicians, etc. Bios can be submitted at sloctheater.org/playbill. Bio parameters: Bios should be in 3rd person and should not exceed 75 words (Director, Producer, Music Director and Choreographer can go up to 150 words). It is suggested that you highlight any previous SLOC participation in addition to roles with other companies, personal interests and/or interesting tidbits. Avoid any cryptic messages or inside jokes. When listing the title of a show that you have been in, please DO NOT USE QUOTATION MARKS. If you are under 18 years old, do not list your age, grade, hometown or school.

• A Letter from the Director—should be approximately 350-400 words from the director about the production, the cast, and/or the experience. Examples of past letters can be provided upon request.

• Thank You’s---Anyone that needs to be thanked by SLOC or the production staff---this includes organizations or individuals that have assisted you in some way (donations, sets, costumes, etc).

• Musicians—the name of the musician as it should appear in the program and the instrument(s) they play. If the MD is playing in the pit, please also note that when the list of musicians is sent.

• Scenes and Songs—usually this is listed in the front of the libretto. If the location or time of day for the scenes is not important, we can simply list the musical numbers. Scenes and songs are preferred though.

***Someone from your staff must pick up the printed playbills from Digital XPress, 5 Sand Creek Road, Albany NY, 12205. The Playbill Editor will communicate additional details when a pickup date is confirmed with the printer, but they will generally need to be picked up by 5 pm on Opening Night. The printer will bill SLOC directly, and you will not be asked for payment or need to submit a payment request form. ***

Due Dates

The Addams Family

- All materials due by August 28, 2019

- Final approval draft to the printer by September 13, 2019

Mary Poppins

- All materials due by October 16, 2019

- Final approved draft to the printer by November 1, 2019

9 To 5

- All materials due by December 26, 2019

- Final approved draft to the printer by January 10, 2020

Funny Thing Happened on the way to the Forum

- All materials due by February 19, 2020

- Final approved draft to the printer by March 6, 2020

Bright Star

- All materials due by April 15, 2020

- Final approved draft to the printer by May 1, 2020

Box Office and Tickets

The production staff is allotted 10 complimentary tickets for your production.  It is left to the discretion of the Directors to decide how they will be distributed.  The Box Office Manager will provide 10 individual gift certificates to the Director or Producer approximately 4-6 weeks before opening.

Individual tickets for all shows go on sale August 1, 2019.  Tickets can be purchased online at www.sloctheater.org, by email at tickets@sloctheater.org or by phone at 877-350-7378 option 1. Phone and email inquiries are usually responded to the same day or within 24 hours.  The box office is only staffed 90 minutes prior to a performance.

A 20% group discount is available for groups of 10 or more seats to the same performance using the same method of payment.  Group tickets cannot be purchased online.  Please contact the box office directly.

Curtain Speech Requirements

There are no specific requirements as to whether or not the curtain speech is done live or pre-recorded, done in character or not.  However, it must be done for each performance and must include the following information:

A welcome to Schenectady Light Opera Company and which season we are in

The title of the show

Information about concessions in the rear of the theater

15 minute intermission

The rest of the shows in the season

Information about exits in case of an emergency

No cell phone use

No recording of any kind

Please contact the Artistic Director if you have any questions or concerns regarding the speech

CLEANUP DAY

Contact: Technical Director

Takes place the Saturday before Opening Night. All cast and crew required to attend. The list of duties includes:

● Empty all garbage containers (audience lobby, backstage, concession area, connector, kitchen, etc)

● Front of House

o Remove any construction materials including screws that will damage vacuum cleaner

o Use the shop vac near front of stage for final junk/screw removal

o Clear of debris and dust railings, balcony ledges, chairs, window sills, etc. o Vacuum aisles, seating areas (including all balconies), stairs, café area and lobby

o Set risers and chairs according the season brochure seating layout.

o Clean and set up concession area, including behind the counter

o Clean lobby restrooms and make sure all plumbing is functional

● Backstage

o Clear wings of any construction materials for any fire inspection

o Move costumes not needed to Ed Building

o Move construction materials and tools to proper storage areas (Taurus Rd or tool closet)

o Neaten up the tool closet

o Vacuum, dust and wipe down all wing surfaces

o Put paints and tools away neatly and away from sprinkler system for fire code and inspection

o Clean and vacuum back stage, including the bathroom

o Organize costumes racks, quick change spots, prop tables, safety lighting, mic station, etc.

● Education Building

o Remove all trash, debris and neaten up rehearsal space and kitchen

o Wipe down main kitchen surfaces

o Set up make-up and hair prep stations in first floor hallway

o Set up costume area in the 2nd floor costume area if needed.

o Set up hall on 2nd floor for cast warm ups and sitting area if needed

● Connector & Lobby

o Vacuum and wipe down railings and sills

o Clean connector hallway windows

o Set up cast and crew boards, and remove all extraneous staples, tape, etc.

PERFORMANCES

WHO’S IN CHARGE AND WHAT DOES THAT MEAN?

During Performances (in order of authority):

1. House Manager 2. Stage Manager 3. Producer 4. Director 5. Music Director 6. Other staff, as designated by the House Manager, Stage Manager, Producer, or Director

The person in charge is responsible for the following:

● Opening a building

o Turn on lights in areas of the buildings which will be used

● Using a building

o Making sure all work follows safety protocols o Making sure the facility is not damaged, including but not limited to structural integrity, plumbing,

electrical systems and finish work (paint, carpets, polished wood, etc.) o Making sure, with the help of the rest of the team, that no unauthorized persons enter o Filing any incident or accident reports o Ensuring the team provides all minor housekeeping tasks necessary to keep the space in safe and neat

order and that public spaces are always appropriate for public view

● Closing a building

o Make sure no one is left in the building o Turn off all but the necessary ghost/running lights (get training from Artistic Director) o Confirming that all entrances are locked

OPENING NIGHT

Contact: Director of Audience Services

The Board President typically has a welcome curtain speech and invites all audience members to join the cast and crew after the show for the opening night party in the Education Building.  The day of the party, the cabaret room and kitchen in the education are off limits for rehearsals.

VIDEOS

Contact: Artistic Director

Rules for performance videotaping (either for archival purposes or to share with the cast and crew) are dictated by the license agreement with each licensing company. SLOC does not arrange for the videotaping of its productions. Contact the Artistic Director with questions.

CABARETS

Contact: Artistic Director

Each show may offer a free post-show cabaret performance in the café area following the Saturday night performances when possible. Audience members are invited.  Someone from the cast/crew must coordinate the Cabaret signup and schedule. When possible, the MD is encouraged to act as accompanist for the Cabaret. If this is not possible, there may be a volunteer available to participate.

WRAPPING IT UP

STRIKE & CAST PARTY Contact: Technical Director

Strike occurs immediately after final curtain of closing performance. All cast and crew are required to participate in strike. It is recommended that the production team provides food for strike.

The incoming show is typically on-site for their initial load-in. Please coordinate these efforts with the incoming Producer and Director.

Cast parties are highly encouraged and left at the full discretion of the production team. If you want to use a SLOC facility for this party, your Producer should arrange the use of this space with the Audition Coordinator or Business Manager (who manage the building use calendar). Please avoid final performance/strike day as this is already a very long day for cast & crew.

CAST & CREW FEEDBACK SURVEY

Contact: Artistic Director

The Artistic Director will send a digital cast/crew survey in the weeks after auditions, mid-rehearsal process and after closing. These results are anonymous and for Board members only. It is at the Board’s discretion if any results are shared with the production team.  Typically a summary of results is shared with the production team as needed and during post-mortems.

PRODUCTION RECOGNITION

Contact: Production Recognition Coordinator and Artistic Director

The Producer, Director, Music Director and Choreographer of each production is recognized by the Company with a gift. The Producer should coordinate the list of names with the Production Recognition Coordinator. The gifts are generally presented at the post-strike party by the Board President or other representative of the company.

T-SHIRTS

The Company does not provide or arrange for t-shirts for the productions. T-shirts and other promotional materials can be arranged by the production staff directly with vendors.

SCHENECTADY LIGHT OPERA COMPANY

BOARD & LEADERSHIP JOB DESCRIPTIONS

PRESIDENT

| Duties: | Time Frame: |
| --- | --- |
| Chair each meeting of the Board of Directors | Monthly |
| Appoint chairs of each department, subject to the approval of the Board | Yearly |
| Visit auditions and/or read through of all productions to welcome people on behalf of the company | Beginning of each show |
| Present production teams with recognition gifts at cast party | End of each show |
| Sign documents on behalf of the company as needed | Ongoing |
| Respond to complaints or other communication directed toward the company as needed | Ongoing |
| Appoint members of the nominating committee for Board elections | By March 1 each year |
| Serve on the awards committee to select recipients for annual awards | March-April each year |
| Present awards at annual meeting | Each June |
| Serve as an administrator on the Facebook page | Ongoing |
| Present revisions of Production Handbook to Board | Yearly |
| Make purchases with SLOC Administration Pex Card | Ongoing |
| Manage Google Apps configuration, membership, etc. | Ongoing |

VICE-PRESIDENT

| Duties: | Time Frame: |
| --- | --- |
| Fill in for the President as needed and requested | Ongoing |
| Chair awards committee to select recipients for annual awards | March-April each year |
| Serve as point of contact for Facilities Chair | Ongoing |
| Manage applications for grants and other funding | As needed |

TREASURER

| Duties: | Time Frame: |
| --- | --- |
| Compile financial reports | Ongoing |
| File 990 reports | Ongoing |
| File sales taxes | Mid-March each year |
| Advise on accounting standards | Ongoing |
| Sign tax exempt forms | Ongoing |
| Review financial data for irregularities | Ongoing |

SECRETARY

| Duties: | Time Frame: |
| --- | --- |
| Prepare and distribute minutes from each Board meeting | Monthly |
| Prepare and distribute packet of leadership reports prior to each Board meeting | Monthly |
| Put together agenda for each Board meeting (included in packet) | Monthly |
| Prepare official notice of annual meeting | 45 days prior to meeting |
| Prepare and receive absentee ballots for annual election | 15 days prior to meeting |
| Handle engraving of annual awards | 15 days prior to meeting |

BUSINESS MANAGER

| Duties: | Time Frame: |
| --- | --- |
| Verify for authorization & sales taxes, sign checks, stamp & take to Post Office | Weekly |
| Check for incoming checks and make deposit once a week. Report to accountant | Weekly |
| Verify cash & checks from Box Office, 50/50, etc. & make deposits. Report to accountant | Mondays after shows |
| Ensure tax exemptions are adequately filed | Ongoing |
| Negotiate & monitor insurance contracts & process claims | Annually/as needed |
| Monitor long term investments | Annually |
| Manage SLOC calendar, schedule auditions, rehearsals & meetings | Ongoing |
| Take calls & requests for space rentals. Show property. Negotiate dates & prices and present to Board for approval. Secure signed agreement, copies of insurance & payment from renters. Secure staffing people to fulfill contract. | As needed |

ARTISTIC DIRECTOR

| Duties: | Time Frame: |
| --- | --- |
| Provide support & assistance to the staff of each production | Ongoing |
| Coordinate revisions to the Production Handbook with input from department chairs | Annually |
| Appoint & work with coordinators of: Audition Committee, Outreach Committee, Show Recommendation Committee | Annually |
| Recommend board liaison for each show | Prior to each show start |
| Distribute surveys to cast & crew | Throughout each show’s rehearsal period |
| Schedule & host post-mortems with each production team | At the close of each show |
| Hold critiques | At least 10 days from each show’s opening |
| Maintain signed Code of Conduct forms for each cast & crew | Ongoing |
| Maintain piano tuning | As needed |
| Present Production Handbook & hold May/October meetings with producers & directors | Bi-annually |
| Coordinate production recognition gifts | Prior to close of each show |
| Provide summary reports for Board meetings | Monthly |
| Provide summary reports & analysis for semi-annual membership meetings | Bi-annually |

TECHNICAL DIRECTOR

| Duties: | Time Frame: |
| --- | --- |
| Appoint, oversee department heads and manage budgets for the following departments: Lighting, Sound, Set, Set storage, Props, Hair, Makeup | Ongoing |
| Ensures a safe work environment for everyone working with or around the stage and technical equipment | Ongoing |
| Safeguard the technical assets of the theater, including overseeing the use of lighting, sound, communications, set, props, hair, costumes, tools and makeup equipment | Ongoing |
| Supervise on-stage rigging so that it is safe and appropriately supports the show’s design concept | Ongoing |
| Ensure department heads recommend and arrange for equipment repair within budgetary constraints | Ongoing |
| Attends first on-stage rehearsal to orient cast and crew | After each show’s load-in |
| Coordinate with production producer(s) for load in/strike and clean up days to ensure minimum required general items are accomplished | During each show |
| Orient and assist facility renters and visiting organizations | As needed |
| Be available, if required, for design and set up of lighting and sound for facility rentals for a fee | As needed |
| Ensure department heads keep accurate inventory of equipment | Ongoing |
| Facilitate equipment rentals both internally and externally | As needed |
| Provide summary reports for Board meetings | Monthly |
| Provide summary reports & analysis for semi-annual membership meetings | Bi-annually |

FINANCE DIRECTOR

| Duties: | Time Frame: |
| --- | --- |
| Manage committee meetings (scheduling, agenda creation, notes) | Monthly |
| Provide summary reports for Board meetings | Monthly |
| Serve as contact person with season’s producers or show budget proposals (provide instructions & annual guides, set submission deadlines, etc) | As needed |
| Oversee required annual reporting by the Treasurer and/or Business Manager (990s, audit, tax-exemption paperwork, etc.) | Annually |
| Provide summary reports & analysis for semi-annual membership meetings | Bi-annually |
| Oversee annual budget process (set deadlines, serve as point of contact for committee chairs, work with committee to prepare to submit draft & final budgets to Board in a timely manor | Annually |
| Support (and change if needed) Business Manager & Accountant in ensuring regular & accurate accounting practices & timely bill payment | Ongoing |
| Oversee organizational expenses to keep in line with annual budget & maintain/grow fiscal health/reserves as agreed upon by Board | Ongoing |
| Create, maintain & update other organizational procedures & documentation as needed (when not covered by other departments) | As needed |
| Journal entries | As needed |

DIRECTOR OF AUDIENCE SERVICES

| Duties: | Time Frame: |
| --- | --- |
| Appoint & Manage: Box Office Coordinator, Usher Coordinator, Opening Night Party Coordinator | Annually |
| Coordinate with production teams regarding impacts or interference with seating layout | As needed |
| Coordinate seating layout with production teams at theater cleanup | During each show |
| Work with Finance Committee to recommend changes in pricing to Board for approval | As needed |
| Approve & distribute comp tickets for charity/fundraising/promotional activities | As needed |
| Serve as an editor & administrator on the Facebook page | Ongoing |
| Handle reciprocal ads to playbill partners | Ongoing |

FACILITIES DIRECTOR

See contract

MEMBERSHIP & VOLUNTEERS DIRECTOR

| Duties: | Time Frame: |
| --- | --- |
| Maintain the record of members eligible to vote | Ongoing |
| Coordinate production of membership newsletter | At minimum bi-annually |
| Prepare & distribute invitations to the annual membership meeting & mid-year meeting | At least 45 days prior to each meeting |
| Work with Board to host annual & semi-annual membership meetings | Bi-annually |
| Coordinate volunteer recognition events | At minimum annually |
| Serve on Awards Committee for selection of annual company awards | March-April each year |

DIRECTOR OF FUNDRAISING & DEVELOPMENT

| Duties: | Time Frame: |
| --- | --- |
| Coordinate sales of ads for playbill | By end of August each year |
| Coordinate fundraising events during performances | During each show |
| Coordinate any special fundraising events produced during the year | As needed |

PUBLIC RELATIONS & ADVERTISING DIRECTOR

| Duties: | Time Frame: |
| --- | --- |
| Maintain Facebook page, including creating posts, responding to private messages, replying to comments (if necessary), creating events (see below) | Ongoing |
| Create events on Facebook, including those for shows & auditions | Beginning of season or within a week of cast list posting; audition events post as soon as dates have been decided |
| Maintain Instagram & Twitter accounts - Create posts, responding to private messages, delegate "take-overs" | Ongoing |
| Send out press releases - see past releases for general template; talk to Director for quote/who to include as "featured" cast members, etc.; update email distribution list as needed | 2 weeks prior to show opening |
| Coordinate artwork for the next season - notify graphic designer when season is confirmed; work with them (and possibly Directors) to make sure art is cohesive and appealing | March/April |
| Coordinate season brochure - once artwork is agreed upon, graphic designer will piece together brochure; PR Chair must create the plot summaries for the brochure, etc., proof President's letter, and proof the final brochure | March/April |
| Coordinate printing of posters, billboard, business cards - Season billboard order in May (to be hung after closing show); Business cards ordered for full season in May; send graphic designer the production team information to finalize posters before ordering, once proofed, they will send the artwork to Media Well Done to print (posters & billboard); should be ordered by the opening night of the prior show | Ongoing |
| Coordinate ad placement (if opportunities arise) ie. Stockade Spy will ask in August-ish, if interested in pursuing an ad; pay for the year and then send the b&w ads to them (all at once) | Ongoing |
| Website maintenance - General maintenance/updates to be made to website (ie. cast lists, announcements about auditions, events); Mary Kozlowski also assists in updating | Ongoing |
| Monitor GoDaddy account - Ensure payments are made to maintain domain, etc. | Ongoing |
| Assist other committees with their marketing needs | Ongoing |
| Coordinate show photo-shoot day(s) - Ask Producer(s) early on in the rehearsal process for 1-2 possible "photo-shoot" days; contact company photographer to schedule | Beginning of each show’s process |
| Coordinate payment/pick up of headshots for production - McGreevy ProLab prints headshots; pay bill with Pex card (or ask Producer to) and coordinate pickup with production team | Ongoing |
| Coordinate tech photographer - Brian Cotterell (Asst Archivist) typically comes the Monday/Tuesday of tech to take photographs unless production team has another photographer coming; always good to send him reminder the week before asking if he's available; if he is not...find replacement to have photos for publicity opening week | Ongoing |
| Oversee purchase of any marketing/promotional materials - tshirts, misc | Ongoing |
| Coordinate show-related appearances/opportunities to do outreach - Organize volunteer opportunities for cast, Greenmarket, Carrot Festival, any events that they could plug the show/theater | Ongoing |
| Coordinate Ann Parillo guest slots - Ann Parillo will contact you well before the season to choose dates; inform Directors of these dates and make sure they know who is attending; complete the guest form (Ann will email you) and submit Friday before air date | Ongoing |
| Coordinate Spectrum News broadcasts - Contact Tamani Wooley with Spectrum News several weeks before opening night to coordinate efforts; someone comes the Sunday of tech to interview and take "b-roll" footage; week of opening Tamani interviews 1-2 people from cast/production team in studio | Ongoing |
| Maintain smaller billboards/frames/powerpoint in lobby/breezeway - Update "SLOC through the years" section with new pictures from archive room/update Powerpoint for television/small billboard should be show-centric/print 8x10 photos (Walmart) of the current show for the frames in the breezeway | Ongoing |
| Media Release Forms - Ensure that all Media Release Forms have been submitted for each production before posting any photos of read-through, etc. Keep track of any cast members that do not want their photo used/released. | Ongoing |

EDUCATION DIRECTOR

CRITIQUE GUIDELINES

Critique is mandatory and will be held for every production.

Critique shall be held no closer than 10 rehearsal days out from tech Sunday

The production team will choose the date, time and any rehearsal day is acceptable

Ideally, all core members from the show will be in attendance including director, producer(s), music director and choreographer. Others from their team are invited by director only.

Following the run, critique will run an hour or less.

There is a worksheet available for teams to use. It can also be altered by the team to better suit their needs if they desire.

Critique will be run by the artistic director or their designee.

The following individuals will be invited to critique by the artistic director or their designee:

1. Board Members

2. Technical Director

3. Producers, directors, music directors and choreographers from other shows from the same

Season.

The director may invite any additional individuals they would like but must inform the artistic director or their proxy of who is attending.

Although members of the show’s production team may attend if invited by the director, they are

expected to not actively participate in critique, regardless of whether or not they are a board member. You’re welcome to take notes and present them to the director at their leisure.

Critique is an opportunity to provide the director with positive and critical feedback. It shall be

completed in a “note giving” context. This is not an opportunity for the critique members to solve problems but to identify the potential concern. It is the discretion of the director as to whether or not they would like additional information at the time or once critique is completed.

Critique Questions

1. Was the plot/story clear?

2. Which characters seemed the most developed? Which characters could benefit

from further development?

3. Which musical numbers were the strongest and most entertaining? Were there

any that needed additional work (concerns with diction, volume, hitting correct

notes, etc.)

4. Which dance numbers were the strongest and most entertaining? Were there

any that needed additional work?

5. Was the stage space used effectively? Any concerns noted?

6. Were you able to understand the actors throughout their scenes?

7. Were the transitions between scenes smooth?

8. Were the relationships believable? Any concerns?

9. How was the pacing of each act? Were there any scenes/numbers that felt

slow?

10. What was a standout scene, number or character?

Schenectady Light Opera Company Production Budget Worksheet

Show: Director: Producer:

Budget Category	Notes/comments	Amount Proposed Orchestra Musicians ($500 ea)                  Enter # requested ‐‐>                                         $	‐ Costumes

Lighting Makeup Props Set Sound

Other (specify)

Total Production Budget	$	‐

Please provide any additional notes/justification for budget request below:

SLOC Fire Extinguisher Locations

Theater

1 at every landing going to sound booth and lighting (3)

1 by main entrance door to theater

1 in basement by furnace

1 by concession area doors to Franklin street

Connector

1 in hallway

1 by main door by ticket booth

1 in basement near furnaces

1 on second floor near boardroom hallway

1 in kitchen of board room

1 in 3rd floor apartment

1 in attic near furnace

Education building

First floor

1 in kitchen

1 by back hobbit door

1 by front liberty door entrance

1 in furnace room

Second floor

1 at each end of hallways (2)

NEB Ballet

2 in dance studios third floor

21 total, serviced yearly by Tri-city fire extinguisher

SLOC Parking lots- Cast and Crew cannot park here during performances

Public Parking

Public Parking

Public Parking

Public Parking

[Grab your reader’s attention with a great quote from the document or use this space to emphasize a key point. To place this text box anywhere on the page, just drag it.]

[Grab your reader’s attention with a great quote from the document or use this space to emphasize a key point. To place this text box anywhere on the page, just drag it.]

Schenectady Light Opera Company VolunteerIntakeForm

Volunteers are the lifeblood of our organization, but we have found that over time, it has been increasingly more difficult to keep track of and keep in touch with the wonderfully talented people that have volunteered with us in the past who may be interested in volunteering with us in the future.

Please complete the information below so that we may properly recognize your efforts in helping us succeed.

Full Name: ____________________________________________________________________________

Home Address: _______________________________________________________________________

City, State, Zip: ________________________________________________________________________

Telephone number: (____) _____-_________

Email Address: ________________________________________________________________________

Are you volunteering for a specific production? If so, which production? __________________________________________________________________________________________

What volunteer activity are performing? ___________________________________________

What volunteer activities are you willing to perform in the future? __________________________________________________________________________________________ __________________________________________________________________________________________

Please note that this form is for volunteers that will NOT submit a biography for the playbill. If you are submitting a playbill biography, this information will be collected from that submission. Non-production specific volunteers only need to complete 1 form per season. Production specific volunteers should complete 1 form per production.

Schenectady Light Opera Company Production Budget Worksheet

Show: There's Something About SLOC Director: Steven Spielberg

Producer: Max Bialystock & Leo Bloom

Budget Category	Notes/comments	Amount Proposed

Music Director ($325)

Orchestra Musicians ($500 ea)	Enter # requested ‐‐> Costumes

Lighting Makeup Props Set Sound

Other (specify)

$	325.00 6 $                 3,000.00

$	1,000.00 $                     400.00 $                       50.00 $                     150.00 $	1,800.00 $                     500.00 $                     100.00

Total Production Budget	$	7,325.00

Please provide any additional notes/justification for budget request below:

We are requesting an extra $100 under the "other" category to provide bodyguards for Leo's blue blanket.

Schenectady Light Opera Company Music Director Agreement

Show Title:

Dates of Performance:

______________________________________________________

______________________________________________________

Performing musicians are a critical element of musical theater performance. This document outlines the obligations of the Schenectady Light Opera Company and the expectations and requirements for

musicians performing with SLOC productions.

Compensation and Payment

●	Compensation as Music Director for rehearsals and a seven-performance run is $550. ●	Compensation as pit musician for rehearsals and a seven-performance run is $550

●	In the case that a performance is cancelled due to weather or any other reason beyond the control of the Company, the compensation amount will be reduced by $50 for each cancelled performance.

●	Likewise, compensation will be reduced by $50 for any unscheduled missed performance due to illness or other reason

●	In the case of expansion beyond seven performances, additional compensation will be set by mutual agreement between the musician and the Company.

●	Payment will be made to the musician in the form of a check presented at the final scheduled performance, as long as the Musician Information Record is completed and returned to the Music Director no later than the Sunday prior to the first performance. If the form is returned after that date, the check will be mailed to the indicated address no later than two weeks following the closing performance.

Expectations for Musicians

●	Attendance at all scheduled rehearsals, as arranged by the Music Director. Musicians may attend additional rehearsals on a volunteer basis in coordination with the Music Director.

●	Attendance at all schedule performances, arriving no less than 45 minutes before the scheduled performance time. ●	Provide own instruments in good working order, unless otherwise arranged with the Music Director in advance

●	Musicians should come to the first rehearsal with sufficient familiarity with the assigned music parts.

●	If a musician is unable to attend a rehearsal or performance and wishes to find a substitute player, they are responsible for negotiating personal payment arrangements with their sub.

Obligations of Schenectady Light Opera Company

●	Music parts will be supplied no less than 4 weeks before the first rehearsal.

●	SLOC is not responsible for normal wear and tear on instruments used in performance, or for consumable supplies (reeds, strings, etc)

●	Payment will be made in the amount and schedule noted above

●	Payment is made for services rendered as a contractor and not as an employee of SLOC. SLOC will not withhold taxes, insurance, or other fees from the payment.

Music Director / Musician Information Record

I am requesting payment of $________ as I did/did not (circle one) participate as a pit musician in addition to my role as Music Director.

Name:

Address:

SSN/EIN:

___________________________________________________________________________________

______________________________________________ City, State, ZIP: ____________________________________________

___________________________________________________________________________________

I agree to the conditions and expectations listed in the Musician Agreement Form

_________________________________________ Printed Name

_________________________________________ Signature

_________________ Date

Schenectady Light Opera Company Musician Agreement

Show Title: ______________________________________________________

Dates of Performance: ______________________________________________________

Performing musicians are a critical element of musical theater performance. This document outlines the obligations of the Schenectady Light Opera Company and the expectations and requirements for musicians performing with SLOC productions.

Compensation and Payment

●	Compensation for rehearsals and a seven-performance run is $550.

●	In the case that a performance is cancelled due to weather or any other reason beyond the control of the Company, the compensation amount will be reduced by $50 for each cancelled performance.

●	Likewise, compensation will be reduced by $50 for any unscheduled missed performance due to illness or other reason

●	In the case of expansion beyond seven performances, additional compensation will be set by mutual agreement between the musician and the Company.

●	Payment will be made to the musician in the form of a check presented at the final scheduled performance, as long as the Musician Information Record is completed and returned to the Music Director no later than the Sunday prior to the first performance. If the form is returned after that date, the check will be mailed to the indicated address no later than two weeks following the closing performance.

Expectations for Musicians

●	Attendance at all scheduled rehearsals, as arranged by the Music Director. Musicians may attend additional rehearsals on a volunteer basis in coordination with the Music Director.

●	Attendance at all schedule performances, arriving no less than 45 minutes before the scheduled performance time. ●	Provide own instruments in good working order, unless otherwise arranged with the Music Director in advance

●	Musicians should come to the first rehearsal with sufficient familiarity with the assigned music parts.

●	If a musician is unable to attend a rehearsal or performance and wishes to find a substitute player, they are responsible for negotiating personal payment arrangements with their sub.

Obligations of Schenectady Light Opera Company

●	Music parts will be supplied no less than 4 weeks before the first rehearsal.

●	SLOC is not responsible for normal wear and tear on instruments used in performance, or for consumable supplies (reeds, strings, etc)

●	Payment will be made in the amount and schedule noted above

●	Payment is made for services rendered as a contractor and not as an employee of SLOC. SLOC will not withhold taxes, insurance, or other fees from the payment.

Musician Information Record (complete and return to Music Director)

Name:

Address:

___________________________________________________________________________________

___________________________________________________________________________________

City, State, ZIP:___________________________________________________________________________________

SSN/EIN:	___________________________________________________________________________________

I agree to the conditions and expectations listed in the Musician Agreement Form.

_________________________________________ Printed Name

_________________________________________ Signature

_________________ Date

Expense/Reimbursement Reconciliation

Use this form to: Report an expense (see Part 1) -OR- to request a check/reimbursement (see Part 2)

__________________________________________________________________________________________________________________ ❒PART 1 - I am reporting an expense that has already been paid for, and no reimbursement is needed (include sales receipt with this form)

Vendor name: _____________________________________________________________________________________________________

Expense description: ________________________________________________________________________________________________

Expense(s) are associated with (check one):

❒SLOC Production / Show

Specify production:_________________________________________________

❒SLOC Company Expense

| Invoice date: ___________ | Invoice #: ______________ | Billing Period: __________ | Amount: _______________ |
| --- | --- | --- | --- |

| Invoice date: ___________ | Invoice #: ______________ | Billing Period: __________ | Amount: _______________ |
| --- | --- | --- | --- |

Submitted by:____________________________________________________________________ Printed Name

_________________________________________________________________________________________________________________ PART 2 - I am requesting payment of expense(s) or reimbursement of expense(s) (include sales receipt with this form)

Vendor name, or name of whom reimbursement check should be made out to: _________________________________________________

__________________________________________________________________________________________________________________

Expense description: ________________________________________________________________________________________________

Expense(s) are associated with (check one):

❒SLOC Production / Show

Specify production:_________________________________________________

❒SLOC Company Expense

| Invoice date: ___________ | Invoice #: ______________ | Billing Period: __________ | Amount: _______________ |
| --- | --- | --- | --- |

| Invoice date: ___________ | Invoice #: ______________ | Billing Period: __________ | Amount: _______________ |
| --- | --- | --- | --- |

Submitted by:_________________________________________________________ Printed Name

Submitted by:_________________________________________________________ Signature

Date submitted: __________________________

SCHENECTADY LIGHT OPERA COMPANY Show Production Budget Worksheet

Updated:

PROPOSED	APPROVED	ACTUAL	NET

| $325.00 $325.00 |  |  |  |  | $0.00 |
| --- | --- | --- | --- | --- | --- |
| $500.00 |  |  |  |  |  |
|  | $0.00 |  |  |  | $0.00 |
|  |  |  | $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 $0.00 |  |  |

Budget Category	Notes/Comments	BUDGET	BUDGET	EXPENDITURES DONATIONS	EXPENDITURES Music Director

Orchestra Musicians, each

Number requested: Costumes

Lighting Makeup/Hair Props

Set Sound

Other (specify)

TOTAL PRODUCTION BUDGET	$325.00	$325.00	$0.00	$0.00	$0.00

| COSTUMES |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| LIGHTING |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| MAKEUP/HAIR |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| PROPS |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| SET |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| SOUND |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

| OTHER |  | Pex Card Total $0.00 Initial Amount: Addition: Addition: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEX SLOC ACCOUNT REIMBURSEMENT DONATION DATE VENDOR ITEM AMOUNT Y/N AMOUNT NAME AMOUNT NAME AMOUNT NAME AMOUNT |  |  |  |  |  |  |  |  |  |  |  |

Schenectady Light Opera Company Code of Conduct

The following outlines the minimal expectations for participants in productions at the Schenectady Light Opera Company:

1. Alcohol and illegal substances - Alcohol may not be consumed in the theater by a cast or crew member at any time, except during organized parties with proper approval. Illegal drugs (including marijuana) are prohibited from the property at all times. Furthermore, cast and crew members should avoid the use of drugs or alcohol prior to a rehearsal or performance as you may pose a safety hazard to you or others around you. If found with any illegal substances on Schenectady Light Opera Company's property, you will be automatically dismissed from the production.

2. Smoking is not permitted on SLOC property at any time

3. Safety – Strictly obey all safety rules and instructions provided by the stage manager, director, or other production designers and crew.

4. Rehearsal attendance – Attend all scheduled rehearsals, unless absence was previously approved by the producer and/or director. For absence due to illness or other emergency, contact the stage manager, producer, or director as soon as possible, but no later than one half-hour prior to the scheduled rehearsal.

5. Punctuality – Plan to arrive early enough that you are ready to go at the scheduled rehearsal time. If delayed due to weather or traffic – within the bounds of safety and applicable traffic laws - contact the stage manager, producer, or director as soon as possible.

6. Cell phones – Silence cell phones when entering rehearsal, and keep them stowed while engaged in rehearsal.

7. Costumes and appearance – Do not make changes in costume, make-up, or hairstyle without approval of the Director or designer. Take proper care of all costumer pieces, including no eating, smoking, or drinking anything besides water while in costume.

8. Backstage noise – During performances and dress rehearsals, all talking between cast and crew is prohibited in the wings, and should be no greater than a whisper in the backstage/dressing room areas. During rehearsal, noise should be limited to the minimum necessary communication between cast and crew.

9. Ad-libs and changes to the script are not permitted without the approval of the director.

10. Care of facilities – Limit food and drink in the theater as much as possible. Dispose of all trash generated in proper bins, and take full trash bins to the dumpster as necessary. Assist in cleaning of bathroom, backstage, and common areas as requested by production staff.

11. Hygiene – Maintain standards of cleanliness and hygiene prior to and during rehearsals and performances. Refrain from scented perfumes, lotions, body sprays, etc. to accommodate the sensitivity of other cast and crew.

12. Professionalism – Maintain a professional and respectful attitude towards the directors, producers, and all members of the cast and crew. Address all disputes privately with the production leadership, or if necessary the Board Liaison

I have read and understand the above expectations, and agree to abide by them for the duration of this production.

___________________________ Printed Name

__________________________ Signature

____________ Date

Schenectady Light Opera Company Code of Conduct – Youth Participants

The following outlines the minimal expectations for participants in productions at the Schenectady Light Opera Company:

1. Alcohol and illegal substances - Alcohol may not be consumed in the theater by a cast or crew member at any time, except during organized parties with proper approval. Illegal drugs (including marijuana) are prohibited from the property at all times. Furthermore, cast and crew members should avoid the use of drugs or alcohol prior to a rehearsal or performance as you may pose a safety hazard to you or others around you. If found with any illegal substances on Schenectady Light Opera Company's property, you will be automatically dismissed from the production.

2. Smoking is not permitted on SLOC property at any time

3. Safety – Strictly obey all safety rules and instructions provided by the stage manager, director, or other production designers and crew.

4. Rehearsal attendance – Attend all scheduled rehearsals, unless absence was previously approved by the producer and/or director. For absence due to illness or other emergency, contact the stage manager, producer, or director as soon as possible, but no later than one half-hour prior to the scheduled rehearsal.

5. Punctuality – Plan to arrive early enough that you are ready to go at the scheduled rehearsal time. If delayed due to weather or traffic – within the bounds of safety and applicable traffic laws - contact the stage manager, producer, or director as soon as possible.

6. Cell phones – Silence cell phones when entering rehearsal, and keep them stowed while engaged in rehearsal.

7. Costumes and appearance – Do not make changes in costume, make-up, or hairstyle without approval of the Director or designer. Take proper care of all costumer pieces, including no eating, smoking, or drinking anything besides water while in costume.

8. Backstage noise – During performances and dress rehearsals, all talking between cast and crew is prohibited in the wings, and should be no greater than a whisper in the backstage/dressing room areas. During rehearsal, noise should be limited to the minimum necessary communication between cast and crew.

9. Ad-libs and changes to the script are not permitted without the approval of the director.

10. Care of facilities – Limit food and drink in the theater as much as possible. Dispose of all trash generated in proper bins, and take full trash bins to the dumpster as necessary. Assist in cleaning of bathroom, backstage, and common areas as requested by production staff.

11. Hygiene – Maintain standards of cleanliness and hygiene prior to and during rehearsals and performances. Refrain from scented perfumes, lotions, body sprays, etc. to accommodate the sensitivity of other cast and crew.

12. Professionalism – Maintain a professional and respectful attitude towards the directors, producers, and all members of the cast and crew. Address all disputes privately with the production leadership, or if necessary the Board Liaison

I have read and understand the above expectations, and agree to abide by them for the duration of this production.

___________________________

Participant Name

__________________________

Parent/Guardian Name

_________________________

Signature

__________________________

Signature

____________

Date

_______________________

Emergency Contact Number